## Disclaimer
Substation Limitations and Committed Solutions
(Ergon Energy Distribution Annual Planning Report 2023)
This workbook forms part of the Ergon Energy Distribution Annual Planning Report 2023 (DAPR) and should be read in conjunction with the report document.
Readers are encouraged to review the details and content as portrayed in the ‘Introduction & Notes’ section of this document in conjunction of with the associated data.
Disclaimer
Ergon Energy’s Distribution Annual Planning Report (DAPR) is prepared and made available solely for information purposes. While care was taken in the preparation of the information in the DAPR, and it is provided in good faith, Ergon Energy accepts no responsibility or liability (including without limitation, liability to any person by reason of negligence or negligent mis-statement) for any loss or damage that may be incurred by any person acting in reliance on this information or assumptions drawn from it, except to the extent that liability under any applicable Queensland or Commonwealth of Australia statute cannot be excluded.
It contains assumptions regarding, among other things, economic growth and load forecasts which may or may not prove to be correct. The forecasts included in the DAPR involve subjective judgements and analysis which are subject to significant uncertainties and contingencies, many of which are out of the control of Ergon Energy. Ergon Energy makes no representation or warranty as to the accuracy, reliability, completeness or suitability for any particular purpose of the information in this document. All information should be independently investigated, reviewed, analysed and verified, and must not be relied upon in connection with any investment proposal or decision. The information contained in the DAPR is subject to annual review. Ergon Energy is obligated to publish future editions by 31st December, in accordance with the National Electricity Rules.
All financials presented in the DAPR or within this document are correct at the time of writing and represent the existing organisational accounting treatment, which may be subject to change. Energy Queensland is finalising the alignment of its Cost Allocation Methodology between Ergon Energy and Energex, potentially impacting the treatment of some Capital and Operational Project costs.
All presented project costings and milestones (as of October 2023) are subject to change.

## Introduction & Notes
Substation Limitations and Committed Solutions
(Ergon Energy Distribution Annual Planning Report 2023)
This workbook provides a listing of projects for which Ergon Energy's network is committed to undertake.
Readers are encouraged to take into account the details and content portrayed in the ‘Introduction & Notes’ section of this workbook when reviewing the the associated data.
All presented project costings and milestones (as of October 2023) are subject to change.
Contents
The tables contained in this spreadsheet include the following information for 50 PoE and 10 PoE in Summer and Winter:
- Substation name and associated limitation that is being addressed
- Impact of limitation on the capacity at transmission-distribution connection point
- Description of committed solution to address the limitation and associated Direct Cost excluding overheads and estimated commissioning date by month and year.
Exclusions
Substation projects that do not meet $1M+ direct cost requirement.

## Substation Committed Solutions
Ergon Energy Substation Limitations and Committed Solutions
Committed projects have reached design and construction phase, and applicable information is listed below.
NOTE: All financials presented in this document are correct at the time of writing and represent the existing organisational accounting treatment, which may be subject to change. Energy Queensland is still finalising the alignment of its Cost Allocation Methodology between Ergon and Energex, potentially impacting the treatment of some Capital and Operational Project costs.
Limitation | Impact of limitation on the capacity at trans-dist connection point | Committed solution to address the limitation
GRAC - Gracemere Zone Substation - Capacity Limitation and Network Security | Rockhampton 66kV Mesh - Pandoin (T061), Rockhampton (T023) and Egans Hill(T127) - No Impact | Gracemere 66/11kV Zone Substation - Target Commissioning - Nov-23 - Cost: $8.4M ± 10%
WETO - West Toowoomba Zone Substation - Asset Condition | H014 Middle Ridge - No Impact | West Toowoomba 11kV Switchboard Replacement 1st Stage - Target Commissioning - Dec-25 - Cost: $14.1M ± 15%
KILK - Kilkivan BSP Bulk Supply - Asset Condition | H005 Woolooga - No Impact on TCP - Removes 132kV tie between Woolooga and Aramara | Kilkivan Bulk Supply - Asset Replacement - Target Commissioning - May-25 - Cost: $29.8M ± 15%
MOSS - Mossman Cassowary - Capacity and Asset Condition Limitation | Turkinje T055/TURK - No Impact | Douglas Shire Reinforcement - Target Commissioning - Aug-25 - Cost: $31.0M ± 15%
GARB - Garbutt Zone Substation - Asset Condition | Garbutt T046/GARB - No Impact | T046 Garbutt 132/66/11kV Substation Asset Replacement - Target Commissioning - Aug-25 - Cost: $23.7M ± 15%
BLAC - Blackwater Zone Substation - Blackwater Substation Interface with Powerlink | Blackwater T032 - No Impact | PLQ CA BLAC Refurbishment - Target Commissioning - Mar-25 - Cost: $5.0M ± 30%
EABU - East Bundaberg Zone Substation - Asset Condition | Wide Bay 132kV Ring - Gin Gin (H006) and Teebar Creek (H063) - No Impact | East Bundaberg Substation Asset Replacement - Target Commissioning - Dec-25 - Cost: $9.6M ± 20%
JAND - Jandowae Zone Substation - Asset Condition | T013 Chinchilla - No Impact | Jandowae Substation Replace 2 CBs 1 TR & 1 VT - Target Commissioning - Jun-26 - Cost: $3.4M ± 15%
TORR - Torrington Zone Substation - Asset Condition | H014 Middle Ridge - No Impact | Torrington Substation Secondary Systems Replacement - Target Commissioning - Aug-25 - Cost: $2.7M ± 30%
NOST - North Street Zone Substation Stage 2 - Asset Condition | H014 Middle Ridge - No Impact | North Street Substation Asset Replacement Stage 2 - Target Commissioning - Nov-26 - Cost: $9.1M ± 15%
MOPA - Mona Park Substation - Asset Condition | Clare South BSP/T193 - No Impact | Mona Park Substation - Asset Replacement - Target Commissioning - Jul-25 - Cost: $6.6M ± 20%
PINN Substation - Asset Condition | H011 Nebo - No Impact | PINN replace 3CTs - Target Commissioning - Oct-24 - Cost: $2.0M ± 15%
BARC Substation - Capacity and Asset Condition Limitation | H015 Lilyvale - No Impact | BARC TR2, 2 x CB and 1 x Prot relay replacement + DC Duplication - Target Commissioning - Feb-25 - Cost: $10.9M ± 15%
HEPA - Hermit Park Substation - Asset Condition | Townsville 66kV Ring - Garbutt (T046), Townsville South (T056), Dan Gleeson (T092) and Townsville East (T094) - No Impact | HEPA replace TR1, CT and CB, protection relays, Install Back up PROT, Build TR Bund, Upgrade fencing - Target Commissioning - Jun-26 - Cost: $4.3M ± 20%
CLER - Clermont Substation - Asset Condition | H015 Lilyvale - No Impact | CLER Asset refurbishment Stage 2 - Target Commissioning - Jul-26 - Cost: $3.3M ± 30%
MERN Meringandan Substation - Capacity and Asset Condition Limitation | H014 Middle Ridge - No Impact | MERN Substation Rebuild - Target Commissioning - Jun 27 - Cost: $11.5M ± 30%
BORE - Boyne Residential - Asset Condition | Gladstone 66kV Mesh - Gladstone North (T074), Gladstone South (T152) - No Impact | Boyne residential 3x RTUs, 66kV CB, 2x RMUs, 3x66kV CTs, Prot Relays - Target Commissioning - Nov-24 - Cost: $2.4M ± 10%
Substation Security Upgrades | Various Substation Sites | Upgrade substation security - Target Commissioning - Sep-24 - Cost: $18.7M± 30%
GEOR - Georgetown Substation - Asset Condition | H13 ROSS - No Impact | Georgetown Replace Protection relay assets - Target Commissioning - Jul-26 - Cost: $3.9M± 15%
Transformer Bunding Priority P0 and P1 | Various Substation Sites | Transformer bunding - Target Commissioning - Mar-24 - Cost: $4.0M± 30%
GUML - Gumlu Substation - Asset Condition | Clare South BSP/T193 - No Impact | GUML Asset replacement - Target Commissioning - Sep-24 - Cost: $3.4M± 15%
CATE - Cairns Terminal - Asset Condition | WOREE (H039) - No Impact | CATE Transformer Cable Upgrade - Target Commissioning - Jun-24 - Cost: $2.2M± 30%
ROGL - Rocky Glenmore - Asset Condition | Rockhampton 66kV Mesh - Pandoin (T061), Rockhampton (T023) and Egans Hill(T127) - No Impact | ROGL Asset Replacement - Target Commissioning - Nov-27 - Cost: $10.1M± 30%
BLAC - Blackwater Zone Substation - Asset Condition and Network Security | Blackwater T032 - No Impact | BLAC Asset Replacement and DC duplication - Target Commissioning - Dec-23 - Cost: $8.4M ± 10%
BUND - Bundaberg Bulk Supply - Asset Condition | Wide Bay 132kV Ring - Gin Gin (H006) and Teebar Creek (H063) - No Impact | Bundaberg Asset Replacement - Target Commissioning - Mar-24 - Cost: $7.7M ± 30%
PIAL - Pialba Substation - Asset Condition | H063 Teebar Creek - No Impact | PIAL New Substation build - Target Commissioning - May-27 - Cost: $18.2M ± 15%
ROSO - Rockhampton South Substation - Asset Condition | T023 Rockhampton - No Impact | ROSO Asset Replacement - Target Commissioning - Nov-26 - Cost: $11.4M ± 30%
GLSO - Gladstone South Substation - Asset Condition | T152 Gladstone South - No Impact | GLSO Asset Replacement - Target Commissioning - Aug-26 - Cost: $7.3M ± 30%
BARG - Bargarra Substation - Protection Limitation | H6 Gin Gin - No Impact | BARG VT Installation - Target Commissioning - Jun-24 - Cost: $0.9M ± 10%